Part B — Section 3: Implementation

Work Plan, Budget, Risk and TRL

Dzvin.co + DIP  |  2026-08-08  |  Grant Application

# 3.1 Work Plan

| WP | Title | Objectives | Lead Deliverables |
| --- | --- | --- | --- |
| WP1 | Management and Governance | Coordination, quality gates, risk governance | Management plan, periodic reports, risk register updates |
| WP2 | Data Foundation and Compliance | Dataset readiness, quality, GDPR/ethics controls | Dataset specs, quality dashboards, compliance dossier |
| WP3 | Decision Intelligence Core | Rule/ML/policy engine, traceability hardening | Architecture releases, decision contract versions |
| WP4 | Explainability and Validation | XAI framework, offline/online evaluation | Evaluation reports, bias audits, reproducibility pack |
| WP5 | Dzvin.co Pilots | Product integration, controlled rollout, user validation | Pilot outcomes, adoption metrics, implementation learnings |
| WP6 | Impact and Exploitation | Dissemination, commercialisation, partner uptake | Impact reports, exploitation roadmap, dissemination outputs |

## WP Dependencies

WP2 gates WP3 and WP4 (data readiness required before model development)

WP3 outputs feed WP5 rollout (decision engine must be stable before pilot)

WP4 evidence informs WP6 impact narrative

# 3.2 Milestones

| ID | Milestone | Month | Success Criterion |
| --- | --- | --- | --- |
| M1 | Baseline and protocol freeze | M3 | Feature spec, dataset spec, evaluation protocol signed off |
| M2 | Hybrid engine v1 validated offline | M6 | H1 status determined; ablation report published internally |
| M3 | Adaptive baseline optimised | M9 | Per-cohort α/ρ; H2 status; calibration error < 0.15 |
| M4 | Clinical concordance verified | M12 | PHQ-9/GAD-7 wiring active; R9-R10 rules operational |
| M5 | Online governance proven | M15 | H5 status; degraded cycle duration reduced vs baseline |
| M6 | Pilot evidence package | M18 | Pilot KPI targets met; reproducibility dossier complete |
| M7 | Platform reuse case | M24 | Second-domain DIP integration; H5 replicated |

# 3.3 Budget Structure

| Cost Category | WP Allocation | Rationale |
| --- | --- | --- |
| Personnel | All WPs (largest share WP2/WP3) | Core R&D, data engineering, ML, product, management FTEs |
| Subcontracting | WP2, WP4 (KNU collaboration) | Academic partnership: statistical validation, theory |
| Cloud/infrastructure | WP3, WP4, WP5 | Model training, evaluation compute, storage, security tooling |
| Travel and dissemination | WP6 | Conference attendance, workshop organisation, publications |
| Indirect costs | All WPs | Per-institution overhead rate as per grant rules |

Note: detailed budget table with EUR amounts to be completed per funding call template.

# 3.4 TRL Roadmap

| Component | Current TRL | Target TRL | Key Evidence Required |
| --- | --- | --- | --- |
| DIP Core (API, rule engine, decision trace) | 4-5 | 6-7 | Pilot-grade reliability, audit trail, governance logs |
| ML Pipeline (training, registry, monitoring) | 3-5 | 5-6 | Reproducible evaluation, drift controls, rollback evidence |
| Adaptive Risk (state vector, minimax, EWMA) | 4-5 | 6 | Offline ablation H1/H2; online governance H5 |
| Explainability Stack | 4-5 | 6 | User trust study H3; faithfulness validation |
| Dzvin.co Integration | 5-6 | 7 | Stable pilot; adoption metrics; reproducibility dossier |

# 3.5 Risk Management

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Insufficient training data for weight optimisation | Medium | High | Synthetic augmentation; transfer learning; conservative fallback |
| PHQ-9/GAD-7 clinical concordance not achieved | Medium | High | Conservative threshold; rules R9-R10 stay inactive; separate study |
| Pilot adoption below target | Medium | Medium | Iterative UX; onboarding playbook; explainability tuning |
| Model drift causes degraded decisions | Medium | High | Auto-mitigation (rules-only mode); trust gating; rollback triggers |
| GDPR compliance gap during pilot | Low | High | DPIA before pilot launch; SOP enforcement; DPO sign-off |

──────────────────────────────────────────────────────────────────────────────────────────

Horizon Europe References:

EIC Work Programme 2026: https://eic.ec.europa.eu/eic-funding-opportunities/eic-pathfinder_en

Funding and Tenders Portal: https://research-and-innovation.ec.europa.eu/funding/how-apply/application-process_en

EIC Pathfinder FAQ: https://eic.ec.europa.eu/eic-frequently-asked-questions/faqs-general-conditions-and-eligibility_en

Evaluation Form: https://ec.europa.eu/info/funding-tenders/opportunities/docs/2021-2027/horizon/temp-form/ef/ef_he-eic-pathfinder-open_en.pdf