Work Packages

Grant Documentation — Dzvin.co + DIP

Dzvin.co + DIP  |  2026-08-08 | Draft

# Work Packages

Мова: Українська (default) | [English](42-work-packages.en.md)

## Document Metadata

Owner: Program Manager

Contributors: All Stream Leads

Version: 0.2

Last Updated: 2026-08-01

Status: Draft

## Purpose

Сформувати структуру Work Packages для реалізації R&D програми Dzvin.co + DIP.

## WP Overview

WP1 Project Management and Governance

WP2 Data Foundation and Compliance

WP3 Decision Intelligence Core (DIP)

WP4 Explainability, Safety, and Validation

WP5 Dzvin.co Integration and Pilots

WP6 Impact, Dissemination, and Exploitation

## WP1: Management and Governance

Objectives: координація, quality gates, risk governance.

Deliverables: management plan, periodic reports, risk updates.

## WP2: Data Foundation and Compliance

Objectives: dataset readiness, quality, GDPR/ethics controls.

Deliverables: dataset specs, quality dashboards, compliance dossier.

## WP3: Decision Intelligence Core

Objectives: rule/ML/policy engine hardening, traceability.

Deliverables: architecture releases, decision contract versions.

## WP4: Explainability and Validation

Objectives: explainability framework, offline/online evaluation.

Deliverables: evaluation reports, bias/safety audits, reproducibility pack.

## WP5: Dzvin.co Pilots

Objectives: product integration, controlled rollout, user validation.

Deliverables: pilot outcomes, adoption metrics, implementation learnings.

## WP6: Impact and Exploitation

Objectives: dissemination, commercialization preparation, partner uptake.

Deliverables: impact reports, exploitation roadmap, dissemination outputs.

## Milestones (Draft)

M1: Baseline and protocol freeze

M2: Hybrid engine v1 validated offline

M3: Controlled online evaluation complete

M4: Pilot evidence package complete

M5: Grant final impact dossier

## Dependencies

WP2 gates WP3 and WP4.

WP3 outputs feed WP5 rollout.

WP4 evidence informs WP6 impact narrative.

## Acceptance Criteria

Кожен WP має measurable deliverables.

Milestones прив'язані до evaluation gates.

Всі критичні міжпакетні залежності явні.

## Links

Related docs: 43-budget.md, 44-risk-management.md, 45-trl-roadmap.md

## Horizon Europe References

EIC Work Programme 2026: https://eic.ec.europa.eu/eic-funding-opportunities/eic-pathfinder_en

Funding and Tenders Portal (application process): https://research-and-innovation.ec.europa.eu/funding/how-apply/application-process_en

EIC Pathfinder FAQ (eligibility and conditions): https://eic.ec.europa.eu/eic-frequently-asked-questions/faqs-general-conditions-and-eligibility_en

Evaluation Form (expert criteria): https://ec.europa.eu/info/funding-tenders/opportunities/docs/2021-2027/horizon/temp-form/ef/ef_he-eic-pathfinder-open_en.pdf

Advice for Applicants: https://rea.ec.europa.eu/guidance/advice-applicants_en

──────────────────────────────────────────────────────────────────────────────────────────

References:

EIC Pathfinder: https://eic.ec.europa.eu/eic-funding-opportunities/eic-pathfinder_en

PARP Ścieżka SMART: https://www.parp.gov.pl/harmonogram-naborow/grants/sciezka-smart